## Sheet1
Dsesign and development of the SMS based Result checking system
| Start Date | Duration (days)
User Interface Design | 2016-08-20 | 8
Database Modelling | 2016-08-29 | 5
Coding | 2016-09-04 | 28
SMS API Integration | 2016-10-03 | 7
Testing | 2016-10-10 | 7
Debugging | 2016-10-18 | 7